## Project Timeline
Athlete Statistics Website Development Timeline
Phase 1: Planning & Setup (2-3 weeks) | Status
Research & Planning
Analyze the source website's structure | FALSE
Document the data points needed for scraping | FALSE
Design your database schema | FALSE
Sketch wireframes for your UI | FALSE
Development Environment Setup
Install required languages and tools | FALSE
Set up version control with GitHub | FALSE
Configure local development environment | FALSE
Phase 2: Basic Implementation (4-6 weeks) | Status
Build Web Scraper
Create scripts to extract data from the source website | FALSE
Implement data cleaning and transformation | FALSE
Test scraper with sample pages | FALSE
Database Implementation
Set up your database (MongoDB or PostgreSQL) | FALSE
Create schemas/models for athlete data | FALSE
Implement CRUD operations | FALSE
Basic Backend
Build RESTful API endpoints | FALSE
Connect scraper to database | FALSE
Implement basic data processing logic | FALSE
Basic Frontend
Create responsive layout | FALSE
Implement navigation and basic pages | FALSE
Connect to backend API | FALSE
Phase 3: Advanced Features (4-6 weeks)
Statistical Analysis
Implement algorithms for relative performance metrics | FALSE
Create leaderboard functionality | FALSE
Build data visualization components | FALSE
User Experience Enhancement
Add filtering and search functionality | FALSE
Implement dynamic updates | FALSE
Optimize performance | FALSE
Automation
Set up scheduled scraping | FALSE
Implement data versioning/history tracking | FALSE
Add monitoring for scraper failures | FALSE
Phase 4: Deployment & Refinement (2-3 weeks)
Deployment
Set up cloud hosting for frontend, backend, and database | FALSE
Configure domain and SSL | FALSE
Implement CI/CD pipeline | FALSE
Testing & Optimization
Test across devices and browsers | FALSE
Optimize loading speeds | FALSE
Fix bugs and edge cases | FALSE
Documentation & Monitoring
Document codebase | FALSE
Set up analytics | FALSE
Implement error logging | FALSE